## Read me
Supplier offboarding checklist
Free template by EvaluationsHub · evaluationshub.com
What it is | A controlled exit for suppliers you are phasing out: notice, open orders, assets and tooling, data, access, final evaluation and transition, so nothing is left exposed.
Lifecycle stage | Exit and offboarding
How to use it
Step 1 | Enter the supplier, exit reason and planned end date at the top. Due days count from the decision date.
Step 2 | Set tasks that do not apply to Not needed. Adjust owners to your organisation.
Step 3 | Update the status as you go. Due dates and overdue flags are calculated.
Step 4 | Close the exit when Ready to close shows Yes, and keep the file with the supplier record.
Legend
Yellow cell | You fill this in (blue text = your input).
White cell | Calculated by a formula. Do not overwrite.
Example row | Realistic sample values showing the expected format. Replace or delete.
Assumption | Task list and due days are a typical sequence. Check notice periods and exit terms in the actual contract.
Run this in EvaluationsHub
Open this template in a free sandbox: https://evaluationshub.co/?utm_source=evaluationshub.com&utm_medium=template-xlsx&utm_campaign=supplier-offboarding-checklist#/signup
Note | This template is a starting point. Adjust weights, thresholds and questions to your own policy. EvaluationsHub automates sending, chasing, scoring and follow-up.

## Checklist
Supplier offboarding checklist
Fill in the yellow cells. Due dates are calculated from the date in B6. Grey columns are calculated.
Supplier | Lumen Packaging Ltd
Exit reason | Consolidation to fewer suppliers
Replacement supplier | Brianza Plastics S.p.A.
Decision date | 2026-11-02
Phase | Task | Owner | Applies to | Due (days from start) | Due date | Status | Done on | Evidence or note | Overdue?
Decision | Exit decision approved and recorded with reason | Head of procurement | All suppliers | 0 | 2026-11-02 | Done | 2026-11-02
Decision | Contract notice period and exit terms checked | Legal | All suppliers | 3 | 2026-11-05 | Done | 2026-11-05
Decision | Notice of termination sent | Category manager | All suppliers | 5 | 2026-11-07 | Done | 2026-11-07
Transition | Transition plan agreed with replacement supplier | Category manager | If applicable | 14 | 2026-11-16 | Not started
Transition | Last-time buy or safety stock agreed | Supply planning | If applicable | 14 | 2026-11-16 | Not started
Transition | Open purchase orders closed or transferred | Procurement operations | All suppliers | 30 | 2026-12-02 | Not started
Transition | Customer or regulatory notification of source change | Supplier quality | If applicable | 30 | 2026-12-02 | Not started
Assets and data | Tooling, equipment and materials returned or transferred | Engineering | If applicable | 45 | 2026-12-17 | Not started
Assets and data | Drawings, specifications and our data returned or deleted, certificate received | IT security | All suppliers | 45 | 2026-12-17 | Not started
Assets and data | System and site access revoked | IT security | All suppliers | 45 | 2026-12-17 | Not started
Finance | Final invoices reconciled and paid | Accounts payable | All suppliers | 60 | 2027-01-01 | Not started
Finance | Open claims, credits and rebates settled | Category manager | All suppliers | 60 | 2027-01-01 | Not started
Finance | Supplier blocked for new orders in ERP | Procurement operations | All suppliers | 60 | 2027-01-01 | Not started
Close | Final evaluation recorded in EvaluationsHub | Category manager | All suppliers | 60 | 2027-01-01 | Not started
Close | Lessons learned captured | Category manager | Strategic and bottleneck | 65 | 2027-01-06 | Not started
Close | Supplier record archived with exit file | Procurement operations | All suppliers | 70 | 2027-01-11 | Not started
Progress | 18.75%
Overdue tasks | 0
Ready to close? | No: 13 tasks open
The first 3 tasks are marked Done as an example. Reset them before use.
Formulas:
Due date = IF(OR(B6="",[Due (days from start)]=""),"",B6+[Due (days from start)])
Overdue? = IF(OR([Due date]="",[Status]="Done",[Status]="Not needed"),"",IF(TODAY()>[Due date],"Overdue",""))