## Read me
Supplier onboarding checklist
Free template by EvaluationsHub · evaluationshub.com
What it is | Every step from approved request to first order and kick-off, with owners, due dates and evidence, so no supplier goes live without the checks your policy requires.
Lifecycle stage | Onboarding and qualification
How to use it
Step 1 | Enter the supplier, segment and start date at the top.
Step 2 | Remove tasks that do not apply, or set them to Not needed. Adjust owners and due days to your process.
Step 3 | Update the status as you go. Due dates and overdue flags are calculated.
Step 4 | The supplier is ready for its first order when Ready to close shows Yes.
Legend
Yellow cell | You fill this in (blue text = your input).
White cell | Calculated by a formula. Do not overwrite.
Example row | Realistic sample values showing the expected format. Replace or delete.
Assumption | Task list and due days are a typical sequence, not a policy. Align them with your own onboarding procedure.
Run this in EvaluationsHub
Open this template in a free sandbox: https://evaluationshub.co/?utm_source=evaluationshub.com&utm_medium=template-xlsx&utm_campaign=supplier-onboarding-checklist#/signup
Note | This template is a starting point. Adjust weights, thresholds and questions to your own policy. EvaluationsHub automates sending, chasing, scoring and follow-up.

## Checklist
Supplier onboarding checklist
Fill in the yellow cells. Due dates are calculated from the date in B6. Grey columns are calculated.
Supplier | Brianza Plastics S.p.A.
Segment | Strategic
Requested by | Sophie Martin, Operations
Start date | 2026-11-02
Phase | Task | Owner | Applies to | Due (days from start) | Due date | Status | Done on | Evidence or note | Overdue?
Request | Approved intake request on file | Requester | All suppliers | 0 | 2026-11-02 | Done | 2026-11-02
Request | Sourcing route completed and award decision recorded | Category manager | All suppliers | 3 | 2026-11-05 | Done | 2026-11-05
Due diligence | Company registration, VAT and bank details verified | Procurement operations | All suppliers | 5 | 2026-11-07 | Done | 2026-11-07
Due diligence | Sanctions and adverse media screening | Compliance | All suppliers | 5 | 2026-11-07 | Not started
Due diligence | Financial health check | Finance | Strategic and bottleneck | 7 | 2026-11-09 | Not started
Due diligence | Self-assessment questionnaire completed and scored | Supplier quality | All suppliers | 10 | 2026-11-12 | Not started
Due diligence | Required certificates collected and in date | Supplier quality | All suppliers | 10 | 2026-11-12 | Not started
Due diligence | ESG questionnaire or rating received | Sustainability | Strategic and bottleneck | 14 | 2026-11-16 | Not started
Due diligence | Information security review | IT security | If applicable | 14 | 2026-11-16 | Not started
Due diligence | Site or remote audit | Supplier quality | High risk only | 21 | 2026-11-23 | Not started
Contract | Contract or framework agreement signed | Category manager | All suppliers | 21 | 2026-11-23 | Not started
Contract | Quality agreement signed | Supplier quality | Strategic and bottleneck | 21 | 2026-11-23 | Not started
Contract | Data processing agreement signed | Legal | If applicable | 21 | 2026-11-23 | Not started
Contract | Code of conduct signed | Category manager | All suppliers | 21 | 2026-11-23 | Not started
Set-up | Supplier created in ERP with payment terms | Procurement operations | All suppliers | 23 | 2026-11-25 | Not started
Set-up | Supplier added to EvaluationsHub with segment and owner | Category manager | All suppliers | 23 | 2026-11-25 | Not started
Set-up | Part numbers, specifications or service levels shared | Engineering or requester | If applicable | 25 | 2026-11-27 | Not started
Set-up | First article or PPAP approved | Supplier quality | If applicable | 35 | 2026-12-07 | Not started
Go live | Kick-off meeting held, contacts and escalation path agreed | Category manager | All suppliers | 28 | 2026-11-30 | Not started
Go live | KPIs, targets and review cadence agreed with the supplier | Category manager | All suppliers | 28 | 2026-11-30 | Not started
Go live | First evaluation scheduled | Category manager | All suppliers | 30 | 2026-12-02 | Not started
Progress | 14.29%
Overdue tasks | 0
Ready to close? | No: 18 tasks open
The first 3 tasks are marked Done as an example. Reset them before use.
Formulas:
Due date = IF(OR(B6="",[Due (days from start)]=""),"",B6+[Due (days from start)])
Overdue? = IF(OR([Due date]="",[Status]="Done",[Status]="Not needed"),"",IF(TODAY()>[Due date],"Overdue",""))