## Read me
Supplier risk register with heat map
Free template by EvaluationsHub · evaluationshub.com
What it is | One register for supplier risks across financial, operational, quality, geopolitical, cyber, ESG and compliance areas, with inherent and residual scores, owners, mitigation and review dates.
Lifecycle stage | Risk management
How to use it
Step 1 | On the Risk register sheet, add one row per risk. Score likelihood and impact from 1 to 5 before and after mitigation.
Step 2 | The score, rating, next review date and overdue flag are calculated. Review intervals are set on the Settings sheet.
Step 3 | The Heat map sheet counts risks by likelihood and impact, so you can see where exposure sits.
Step 4 | Review Critical and High risks with the supplier owner at every business review.
Legend
Yellow cell | You fill this in (blue text = your input).
White cell | Calculated by a formula. Do not overwrite.
Example row | Realistic sample values showing the expected format. Replace or delete.
Assumption | Ratings use likelihood x impact on a 5 x 5 grid: 1 to 4 Low, 5 to 9 Medium, 10 to 16 High, 20 and above Critical. Bands and review intervals are examples you can change on the Settings sheet.
Run this in EvaluationsHub
Open this template in a free sandbox: https://evaluationshub.co/?utm_source=evaluationshub.com&utm_medium=template-xlsx&utm_campaign=supplier-risk-register#/signup
Note | This template is a starting point. Adjust weights, thresholds and questions to your own policy. EvaluationsHub automates sending, chasing, scoring and follow-up.

## Risk register
Supplier risk register
Row 5 is an example. Grey columns are calculated.
Risk ID | Supplier | Category | Risk type | Description | Likelihood (1-5) | Impact (1-5) | Inherent score | Inherent rating | Mitigation | Owner | Mitigation status | Residual likelihood | Residual impact | Residual score | Residual rating | Last review | Next review due | Overdue?
RSK-001 | Brianza Plastics | Direct materials | Single or concentrated source | Only qualified source for sensor housings; tool held at supplier site. | 4 | 5 | 20 | Critical | Qualify second source; move tool ownership into contract; hold 4 weeks safety stock. | Category manager | In progress | 3 | 4 | 12 | High | 2026-10-15 | 2027-01-13
Formulas:
Next review due = IF(OR([Last review]="",AND([Residual rating]="",[Inherent rating]="")),"",[Last review]+INDEX(Settings!$C5:C8,MATCH(IF([Residual score]="",[Inherent score],[Residual score]),Settings!$A5:A8,1)))
Overdue? = IF([Next review due]="","",IF([Next review due]<TODAY(),"Overdue",""))

## Heat map
Risk heat map
Number of risks by likelihood and impact. Choose inherent or residual in B3.
Show | Residual
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 1 | 0
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0
Rating | Inherent | Residual
Critical | 1 | 0
High | 0 | 1
Medium | 0 | 0
Low | 0 | 0
Overdue reviews | 0

## Settings
Settings
Yellow cells are editable.
From score | Rating | Review every (days)
1 | Low | 365
5 | Medium | 180
10 | High | 90
20 | Critical | 30
Risk types
Financial
Supply continuity
Quality
Geopolitical and trade
Cyber and data
ESG and human rights
Compliance and legal
Single or concentrated source
Scale | Likelihood | Impact
1 | Rare: not expected in 3 years | Minor: no customer effect, under EUR 10k
2 | Unlikely: could happen in 3 years | Moderate: short delay, under EUR 100k
3 | Possible: could happen this year | Significant: line stoppage or customer complaint
4 | Likely: expected this year | Major: lost customer orders or regulatory finding
5 | Almost certain: already happening | Severe: production stop, recall or legal action